# NATIVE VETERAN ENTERPRISE COMMAND CENTER

Owner: John Carroll

LLC: Two Mile Solutions (Alaska LLC, Foreign-Registered in Missouri)

Location: Poplar Bluff, Missouri (5 Acres)

# 1. CAPITAL STACK

- Cash from Home Sale: $163,275

- Grants Total: $230,000 (NAAF, USDA, MO Ag, DNR, EPA)

- USDA Loan (eligible fallback): $100,000

# 2. SKELETON SETUP (LOWEST RESISTANCE PROFIT PLAN)

- Land (5 Acres): $54,900

- Used RV: $10,000 (est.)

- RV Pad + Utilities: $5,000

- Prefab Workshop (40x60): $50,000

- CNC Mill + Lathe + 3DP: $32,800

- Metal Shredder + Furnace + Molds: $21,000

- Ag Setup (Chickens, Goats, Garden): $7,000

# 3. GRANT TRACKER

Includes NAAF, USDA SDA/Vet, MO Value-Added, MO DNR, EPA Tribal — all eligible.

# 4. FAST PROFIT STRATEGY

- Generate first revenue within 90 days

- CNC parts, CSA sales, recycled billet loop

- Target channels: Etsy, local markets, direct sales

# 5. NEXT STEPS CHECKLIST

- [ ] MO Sales Tax ID

- [ ] Business License / Registered Agent

- [ ] SAM.gov + UEI + CAGE Code

- [ ] SDVOSB + Native Certifications

- [ ] CNC Install + Product Launch

- [ ] Farm Ops Start + CSA Sale

# 6. FINANCIAL SUMMARY

Total Startup Cost: $180,700

Cash Used: $119,900

Grants Used: $60,800

Cash Remaining: $43,375

Grant Surplus: $169,200

Final Surplus: $212,575

# 7. FINAL NOTES

This is the forged legacy plan to launch Two Mile Solutions into the billion-dollar tier — no fluff, no debt, just build.

# 8. WEEKLY IGNITION PLAN

| Week | Action | Target Outcome |
| --- | --- | --- |
| 1–2 | Land acquisition + business licensing | Legally anchored in MO |
| 3–4 | RV pad setup + prefab install scheduled | Site physically established |
| 5–6 | Grants filed (NAAF, USDA, MO Ag) | Grant pool activated |
| 7–8 | CNC mill + lathe ordered | Manufacturing begins |
| 9–10 | Chicken coop/fence delivered, raised beds built | CSA & ag ops launched |
| 11–12 | ONE LIFE PARTS™ online sales go live | First revenue stream ignited 🔥 |