# TWO MILE SOLUTIONS – LEGACY COMMAND CENTER

Prepared for: John Carroll
Entity: Two Mile Solutions (Alaska LLC, Missouri-Registered)
Location: Poplar Bluff, Missouri

# 1. CAPITAL STACK

- Home Sale Cash Reserve: $163,275

- Grant Pipeline Total: $230,000 (NAAF, USDA SDA, MO Ag, MO DNR, EPA)

- Optional USDA Veteran Loan: $100,000

TOTAL LIQUID: $393,275 (excluding USDA loan fallback)

# 2. LOW-RESISTANCE LAUNCH PLAN

• 5 Acre Land Acquisition – $54,900
• Used RV for On-Site Living – $10,000
• RV Pad & Utilities – $5,000
• Prefab Insulated Workshop (40×60) – $50,000
• CNC Mill + Lathe + 3D Printers – $32,800
• Shredder + Furnace + Billet Gear – $21,000
• Chickens + Goats + Crops – $7,000
Total Startup: $180,700

# 3. FAST-PAYBACK PRODUCT STRATEGY

• Aluminum Spacers – CNC – $12–25

• RC Suspension Arms – 3DP – $25–40

• Billet Keychains – CNC – $10–20

• Weld Tabs – CNC – $20–50 bundle

• CSA Herb Grinders + Egg Racks – Print – $5–15

• Farm Utility Kits – CNC + Print – $25–60

• Mini Tool Trays – Shop Use – $10–30

• Subscription Club Box – Quarterly mailer of billet gear – $25/mo

# 4. SCRAP-TO-BILLET CYCLE

• Local scrap sourced (HVAC, farms, junk)
• Shred → Melt → Mold → Machine
• Marketed as: 'Built from the Land™ – Recycled American Metal'

# 5. GRANT & FUNDING TRACKER

• NAAF – $25K – Livestock & Garden

• USDA SDA – $40K – CNC & Farming

• MO Value-Added Ag – $20K – CNC & Product Line

• MO DNR – $30K – Recycling Shredder

• EPA Tribal Waste – $15K – Metal Reuse System

# 6. MISSION OPS: SYSTEM SURVEILLANCE

- Legal Setup: LLC, Sales Tax ID, Bank, Insurance, SAM.gov

- Equipment Checklist: CNC + Lathe + 3DP + Shredder + Furnace

- Infrastructure: Land secured, shop installed, RV HQ connected

- Tool Stockpile: $2K reserved for endmills, billets, common bar stock

- Invoice & CRM Tracking: Airtable + PDF invoices (Zoho or template)

# 7. IGNITION TIMELINE

• Weeks 1–2: Land acquired, business registered

• Weeks 3–4: RV and prefab shop installed

• Weeks 5–6: Grants submitted, CSA/coop started

• Weeks 7–8: CNCs arrive, billet production begins

• Weeks 9–10: First product hacks listed for sale

• Weeks 11–12: Scrap melted, CSA harvested, income active

# 8. LEGACY OUTLOOK

This plan represents a lean, powerful path to profitability using scrap, land, tools, and American strength. All systems operate on paid equipment, grant funding, and veteran-native resilience.

ONE LIFE PARTS™: Built to Outlast. Powered by Two Mile Solutions.